Frankfort County Health Department

Strategic Plan

| Mission Prevent. Promote. Protect. Franklin County. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Vision Healthy Choices = Healthy Lifestyles |  |  |  |  |
| Values Competent, Accessible, Progressive, Trustworthy, Compassionate, Knowledgeable |  |  |  |  |
| GOAL 1 Enhance public health education initiatives through effective partnerships |  |  |  |  |
| Strategies | Tactics | Time frame | Who initiates | Measure of progress |
| Evaluate and enhance health education initiatives | Evaluate scope of existing educational initiatives in the Business Office, Environmental, Community Health Education, Clinic, Home Health, Preparedness, and Accreditation departments | Feb. 2012 | Management Team | Have evaluation plan in place Timeframe extended due available resources. Will be added to Executive Committee agenda. |
|  | Assess feasibility of current programs | April 15, 2011 Will reassess in April 2012 with FY 13 budget. | Management Team | List of programs of FY 2012 planning and budget FY 12 budget completed with list of programs June 2011. |
| In collaboration with partners, develop and implement a community health improvement plan | Convene a summit of community health partners | Aug. 2, 2010 | Judy Mattingly | Meeting Minutes Draft was presented to MAPP on June 30, 2011 and revised Sept. 8, 2011. |
|  | Develop common goals for a community health improvement plan | Aug. 2, 2010 | Judy Mattingly | List of strategic issues Goals were developed from April – July 2010. |
|  | Define the actions (programs, policies, processes) required to implement these goals and set priorities for action | Nov. 2010 Health improvement plan will be updated for July 2012 MAPP meeting. | Judy Mattingly | List of selected strategies MAPP used a nominal group technique July 2010 to prioritize strategies. Strategies were revised June 2011. Progress has been made on several health improvement plan strategies. |
|  | Evaluate current partnership activities and programs that support the community health improvement plan for effectiveness and for value to each partner | Aug. 2011 March 2012 Evaluation of all health improvement plan strategies is ongoing, performance measures will be updated for July 2012 MAPP meeting. | Judy Mattingly | Completed evaluation forms TAKE 10 evaluations completed May 2011. Oral health services evaluated June 2011. Other strategies will be assessed by March 2012. |
|  | Identify each partner's strengths and assets they are willing to commit to the implementation of these actions | Jan. 2011 | Judy Mattingly | Completed Community Health Improvement Plan with responsible parties Completed Sept. 8, 2011. New partners added with ACHIEVE funding. |
|  | Develop an agreement on shared responsibilities and recognitions for joint programs | Jan. 2011 | Judy Mattingly | Completed Community Health Improvement Plan with responsible parties Completed Sept. 8, 2011. |
|  | Develop a complete listing of partnership educational programs | Feb. 2011 | Management Team | List of partnerships Partners and programs listed in community health improvement plan. |
| Continue to support and participate in designated community health initiatives (e.g., Pioneering Healthy Communities) | Implement policy in school to increase physical activity (TAKE 10!) | Sept. 2010 July 2011 | YMCA PHC Team | TAKE 10! materials delivered Completed teacher evaluations Completed May 2011. Will use school nursing BMI data along with teacher survey to evaluate future years. |
|  | Develop decision criteria for participation in community health initiatives | Sept. 2010 Reassess during FY 13 budgeting | Community Health Education Team with Management Team | Completed decision tree (flow chart) Presentation request form developed and in use since Sept. 2010. Add to Director’s Team meeting agenda. |
| Identify and capture new opportunities to encourage healthy and safe lifestyles in the community | Evaluate opportunities to maximize the physical activity opportunities of local community development projects | Feb. 2012 | MAPP | Participation in meetings (meeting minutes) Goal in community health improvement plan, |
| GOAL 2 Maximize the quality and effective delivery of Health Department services and programs |  |  |  |  |
| Strategies | Tactics | Time frame | Who initiates | Measure of progress |
| Develop a quality improvement plan | Utilize the accreditation process to develop quality and accountability measures | Feb. 2011 | Accreditation and Management Teams | Completed draft of overall QI plan approved by Board of Health (BOH) QI Plan completed April 4, 2011. Will be presented to Board of Health Oct. 2011. QI Plan updated Jan. 30, 2012. |
|  | Monitor and evaluate quality and scope of services from the perspective of clients throughout FCHD | Feb. 2011 2013 will conduct agency contribution questionnaire in conjunction with NPHPSP. | Management Team | Completed surveys and analysis of surveys Home Health and Clinic satisfaction surveys in place. Quality of Life survey conducted Nov. 2009. Executive committee will explore other tools for evaluation. |
|  | Clarify desired outcomes from participation in partner educational programs | April 2011 | Management Team | Report of desired outcomes Goals and objectives in community health improvement plan. |
| Address cultural and language barriers affecting access to services | Explore feasibility of a national culturally competency certificate | June 30, 2012 Complete “Health Inequities” series early FY 13. | Accreditation Team | List of pros and cons of this certification (Force Field Analysis) Awaiting DPH guidance for inclusion in workforce development plan. Have been showing the “Health Inequities” series since July 2011. Two “Health Inequities” series remaining. Exploring NACCHO cultural competency online course. Accreditation Coordinator will participate in a training offered by Lex. HD in March 2012. |
|  | Contact minority civic and neighborhood associations to build a better understanding of the nature of language and cultural barriers | July 2011 | Accreditation Team | List of organizations In All Hazards Plan completed Aug. 2011. MAPP is identifying community leaders in our Hispanic community. |
| Clarify the authority of the Environmental Division to respond to violations | Market and advertise scope of environmental health authority | Sept. 2011 Ongoing | Environmental and Management Teams | Annual communications Annual Report distributed Sept. 2011. Ongoing website updates and newspaper articles. Letters have been sent to city code enforcement. Compliant form instituted Aug. 2010. Overall number of complaints have decreased. |
| Expand School Nursing program. | Continue monitoring Medicaid billing services. | FY 13 | Management Team and Board of Health | CDC gold standard of 1 school nurse for every 750 students. Widespread support of program from schools and BOH with current school nurse placement as of Jan. 2012. |
| GOAL 3 Strengthen participation in local and state public policy process |  |  |  |  |
| Strategies | Tactics | Time frame | Who initiates | Measure of progress |
| Increase engagement of FCHD BOH | Complete National Public Health Performance Standards Program Local Public Health Governance Performance Assessment Instrument | Aug. 2012 NPHPSP results will be presented to BOH in May 2012. | Management Team | Completed National Public Health Performance Standards Program Local Public Health Governance Performance Assessment Instrument Will field test NPHPSP governance tool by Nov. 2011. Board of Health approved this field test Aug. 2011. NPHPSP was completed in Oct. 2011 & results received March 2012. Will prioritize goals based on results. Dr. Hoover and Judy Mattingly will provide a presentation with the CDC at the Aug. 2012 NALBOH meeting. Internal stakeholder survey conducted Jan. 2012. |
|  | Provide evidence based on measures we collect to inform public policy development | Aug. 23, 2010 Ongoing | Management Team | Quarterly updates at BOH meetings (meeting minutes) TAKE 10, Oral Health and Tobacco Free Schools presented Aug. 2011. |
| Develop relationship with Planning and Zoning | Host an informational meeting with Planning and Zoning | Dec. 2010 Ongoing | Paula Alexander | Meeting minutes Eric Cockley has attended ACHIEVE meetings. Robert Hewlett has attended Y PHC meetings. |
|  | Attend Planning and Zoning meetings | Jan. 2011 | Community Health Education and Environmental Teams | Attended meetings (meeting agendas and minutes) Paula will determine list of Planning and Zoning meeting dates and times by Sept. 2012. |
|  | Health Impact Assessment | Fall 2012 | Director’s Team | Three staff members attended HIA workshop Aug. 2011. |
| GOAL 4 Enhance organizational capacity to efficiently and effectively address mission |  |  |  |  |
| Strategies | Tactics | Time frame | Who initiates | Measure of progress |
| Complete the accreditation process | Complete Community Health Improvement Plan, Community Health Status Assessment, Strategic Plan and QI Plan | Fall 2011 Anticipating PHAB site visit late FY 12. | Accreditation Team | Completed Community Health Improvement Plan, Community Health Status Assessment, Strategic Plan and QI Plan Completed requirement Sept. 8, 2011. Awaiting PHAB application. Application was submitted and accepted in Oct. 2011. |
| Develop a staffing plan | Review and update all staff positions | Dec. 2011 and annually thereafter July 1, 2012 | Management Team | Updated job descriptions for all staff All employees will receive updated job description during FY 12 evaluation. |
|  | Evaluate and modify the current evaluation process | Jan. 2011 July 2011 | Management Team | Notify state Implement new evaluation process Began new evaluation July 1, 2011. |
|  | Develop succession plan | July 2012 | Management Team | Completed succession plan Awaiting UK Public Health Training Center schedule. Have also shared with this interest with DPH. |
| Strengthen internal and external communications through a marketing plan | Identify and define the characteristics of key external stakeholder audiences | Aug. 2010 | Judy Mattingly | List of stakeholders Completed Sept. 8, 2011 with community health improvement plan. |
|  |  |  |  | Included under goal 2. |
|  | Enhance internal communications to increase knowledge about the Health Department across all sectors | Aug. 2010 Aug. 2012 | Management Team | Completed employee surveys and analysis of results Used results of employee surveys conducted July 2010 for the development of strategic plan. |
|  | Develop an internal and external communication plan | Dec. 2012 | Accreditation and Community Health Education Teams | Completed internal and external communication plan approved by BOH Communication plan presented to BOH and approved Jan. 2012. |
|  | Consider other ways to increase internal communications including rotating interdisciplinary teams | Sept. 2010 | Margie Bucklew and Management Team | Presentation to Management Team Formed interdisciplinary Director’s Team Jan. 2011. An Interdisciplinary QI Team is addressing grant funding. |
| Move toward a paperless management system | Research other public health departments who have gone paperless | Dec. 2012 | Rondia Burdine, Margie Bucklew and Business Office Team | Research completed and presented to Management Team Pay, travel and news and views all electronic. Have researched electronic medical records, but there are significant financial barriers. Awaiting DPH guidance. |
| Develop long-term financial plan that maximizes provision of resources to meet community health needs | Research Local Health Department financial planning models | July 2011 | Paula Alexander, Ken Fiser and Management Team | Completed report of research and presentation to BOH Completed FY 12 budget and plan, which included the elimination of requests and programs. Also serving on national PHUNDS workgroup. |
|  | Increase grant funding | FY 13 | Get ‘er Funded QI Team | QI team has been formed and is implementing a FCHD grant toolkit and tracking grant funding. |
| Support professional development of staff | Tuition reimbursements if funding becomes available | April 2011 | Paula Alexander, Ken Fiser and BOH | Presentation to BOH and BOH decision Continue to look for ways to offer this reimbursement. |
|  | Incorporate professional development into performance review | Dec. 2011 & annually thereafter | Paula Alexander and Management Team | Completed evaluations containing professional development plan Workforce development plan is begin drafted. Workforce development plan completed. Will participate in DPH workforce needs assessment on TRAIN beginning April 2012. |
| Periodically review and revise as needed the strategic plan | Incorporate periodic review and revisions of strategic plan into Accreditation and Management Team meeting agendas | Every 18 -24 months | Accreditation and Management Teams | Revised strategic plan Reviewed and revised strategic plan on Sept. 12, 2011. Revised Jan. 24, 2012. |